## Slide 1
Home Work Package
Cash Flow Plan for 36 Months
03 Sept 2026
Cash Flow Planning 1

## Slide 2
Develop your Cash Flow Plan
Develop your Cash Flow Plan
Depending on stage of your Journey – You may or may NOT have Revenue.
REVENUE
COST
CASH
If no Revenue, proceed with Cost.
Cash Flow Planning 3

## Slide 3
CASH FLOW PLANNING
Develop your Cash Flow Plan - More Importantly
Cash Flow Planning 6
Source of Funds / Cash Inflows
  Grants
  Subsidies
  Loans
  Equity — internal
  Equity — external
2 Cash Outflow
Use the cash flow planning tool calculate
OPERATING / PROJECT COSTS
And
SPECIALIST / PROGRAMME COSTS
3 Decision-ready Cash Flow plan
Build a cash flow view that supports funding, runway and milestone decisions.
Output: a living plan that can be updated as evidence and timing change.

## Slide 4
FUNDING STRATEGY
Source of Funds / Cash Inflows
Grants
From various sources – Institutions, Corporates or any other source.
Subsidies
For Innovation / Product Design / Capex & many more.
Loans
External or Internal Loans
Equity — internal
Founder / shareholder capital
Equity — external
Investor capital linked to future value creation
Funding is the fuel that lets the business model reach proof points.
15

## Slide 5
CASH OUTFLOWS
Know what consumes cash — and when
OPERATING / PROJECT COSTS
• Manpower / salaries
• Rent / utilities
• Equipment
• R&D supplies
• Contracted services
• CRO services
SPECIALIST / PROGRAMME COSTS
• cGMP
• Legal & professional
• Patent prosecution
• Travel
• Other operating costs
11
Focus on timing, not only totals: a large one-off payment can create a runway shock.

## Slide 6
Develop your Cash Flow Plan
Roadmap → Action Plan → Resource Plan → Cash Flow.
Roadmap → Action Plan → Resource Plan → Cash Flow
Cash Flow Planning 4

## Slide 7
FINANCIAL MANAGEMENT
Connect roadmap, action, resources and build the cash flow plan
Each planning layer changes the next.
ROADMAP
ACTION PLAN
RESOURCE PLAN
CASH FLOW
Cash Flow Planning 5

## Slide 8
CASH FLOW PLANNING
Build the cash flow plan
Cash Flow Planning 6
1 Resource requirements
Translate the roadmap into the people, facilities, equipment and services required to execute.
2 Planning workbook
Use the cash flow planning tool to map timing and amount of each resource need.
3 Decision-ready plan
Build a cash flow view that supports funding, runway and milestone decisions.
Output: a living plan that can be updated as evidence and timing change.

## Slide 9
Develop your Cash Flow Plan
Your Homework
Develop your Cash Flow Plan
And
Make presentation of following slides
Cash Flow Planning 3

## Slide 10
Cash Flow Plan – Cumulative Cash Flow.
From your cash flow plan. These should be same numbers as appearing in your cash flow plan sheets.
Illustrative numbers shown — replace with your figures from the Excel sheet.
Amount in Thousands of $ ($256000 will be just 256K in this sheet)
At the end of 6 Months
At the end of 12 Months
At the end of 18 Months
At the end of 24 Months
At the end of 30 Months
At the end of 36 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40).
145.1K
309.2K
475.3K
665.0K
889.9K
1107.8K
Total Cumulative Funding Available up to this Month $ (As per Row 40).
150.0K
400.0K
400.0K
650.0K
650.0K
650.0K
Cumulative Cash at end of each Month. (As per Row 43).
4.9K
90.8K
-75.3K
-15.0K
-239.9K
-457.8K
Key Milestone Delivered at end of each period.
10 trial systems purchased; prototype testing underway
Trial deployments begin; outsourced developer onboarded
10 customer-site trials completed
Implementation hire planned; redeployment review
Sales / operations hire planned; trial fleet reused
Runway review and prepare revenue launch
Cash Flow Planning 9

## Slide 11
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 6 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 1–6
Funding: S$100K founder equity in Month 1 and S$50K unconfirmed grant in Month 6.
Includes S$15K for ten reusable trial systems, prototype testing/tweaking and initial trial preparation.
Cumulative costs: S$145.1K; closing cash: S$4.9K.
Milestone: trial fleet purchased and prototype plan established.
Cash Flow Planning 10

## Slide 12
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 12 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 7–12
Outsourced Indonesia technical developer starts in Month 7. Ten customer-site deployments begin from Month 4 and continue through Month 13; local and Indonesia travel included.
Cumulative costs: S$309.2K; closing cash: S$90.8K.
Milestone: trial deployments underway and developer onboarded.
Cash Flow Planning 11

## Slide 13
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 18 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 13–18
Final trial deployments and redeployment/testing costs are completed. No additional funding assumed.
Cumulative costs: S$475.3K; closing cash: -S$75.3K.
Milestone: ten customer-site trials completed.
Cash Flow Planning 12

## Slide 14
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 24 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 19–24
Singapore implementation/customer-success hire starts in Month 19; S$250K external-equity target in Month 24. Reusable trial fleet supports further validation.
Cumulative costs: S$665.0K; closing cash: -S$15.0K.
Milestone: implementation capacity and redeployment plan reviewed.
Cash Flow Planning 13

## Slide 15
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 30 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 25–30
Singapore sales/operations hire starts in Month 25; Indonesia supplier/developer travel continues.
Cumulative costs: S$889.9K; closing cash: -S$239.9K.
Milestone: trial fleet reused while preparing commercial scale-up.
Cash Flow Planning 14

## Slide 16
Cash Flow Plan — Cumulative Cash Flow
Illustrative values • Replace with your Excel numbers
Amount in Thousands of $ ($256000 will be just 256K in this sheet) | At the end of 36 Months
Total Resources Requirements Cumulative Cash Flow $ (As per Row 40). | 
Total Cumulative Funding Available up to this Month $ (As per Row 40). | 
Cumulative Cash at end of each Month. (As per Row 43). | 
Key Milestone Delivered at end of each period. | 
Months 31–36
No additional funding assumed. No customer revenue or customer COGS is modelled in this coursework case.
Cumulative costs: S$1,107.8K; closing cash: -S$457.8K.
Milestone: secure next funding before revenue launch.
Cash Flow Planning 15

## Slide 17
INTEGRATED CONTROL LOOP
Manage the cash plan as a system
LEARNING LOOP
EXECUTION + FUNDING LOOP
Evidence updates the assumptions; the plan updates the resources and cash requirements.
ASSIMILATE
UNDERSTAND
REFLECT / REVIEW
DECIDE
ROADMAP
ACTION PLAN
RESOURCE PLAN
CASH FLOW
Cash Flow Planning 16

## Slide 18
Cash Flow Plan – Cumulative Cash Flow.
Please keep your Excel sheets of
Action & Resources Plan ready as back up for any questions / clarifications during the presentation.
As well Cash Flow Plan sheet ready as back up for any questions / clarifications during the presentation.
Cash Flow Planning 17